## Basic Gantt Chart
RADTEL
| TASK NAME | START DATE | END DATE | START ON DAY* | DURATION* (WORK DAYS) | TEAM MEMBER | PERCENT COMPLETE | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8
Employee Module
| Employee Registration | 2019-11-22 | 2019-11-23 | 0 | 2 |  | 0%
| Employee Login & logout | 2019-11-25 | 2019-11-25 | 3 | 1 |  | 0%
| Forgot password | 2019-11-25 | 2019-11-25 | 3 | 1 |  | 0%
| Change password | 2019-11-27 | 2019-11-27 | 5 | 1 |  | 0%
| Account settings | 2019-11-27 | 2019-11-30 | 5 | 4 |  | 0%
| Apply scholarship | 2019-12-02 | 2019-12-03 | 10 | 2 |  | 0%
| Scholarship Status | 2019-12-04 | 2019-12-05 | 12 | 2 |  | 0%
School Management
| School Registration | 2019-12-06 | 2019-12-07 | 14 | 2 |  | 0%
| School Registration status | 2019-12-07 | 2019-12-07 | 15 | 1 |  | 0%
| HR Manger Registration | 2019-12-09 | 2019-12-10 | 17 | 2 |  | 0%
| HR Manger Login | 2019-12-10 | 2019-12-10 | 18 | 1 |  | 0%
| HR Manger Forgot password | 2019-12-10 | 2019-12-10 | 18 | 1 |  | 0%
| HR Manger Change Password | 2019-12-10 | 2019-12-10 | 18 | 1 |  | 0%
| HR Manger Account Settings | 2019-12-12 | 2019-12-14 | 20 | 3 |  | 0%
| Create Hr | 2019-12-16 | 2019-12-16 | 24 | 1 |  | 0%
| View Scholarship Request | 2019-12-17 | 2019-12-17 | 25 | 1 |  | 0%
| Approve or Reject Scholarship Request | 2019-12-17 | 2019-12-17 | 25 | 1 |  | 0%
| Approved Student and reject student list | 2019-12-17 | 2019-12-17 | 25 | 1 |  | 0%
Company
| Company Registration | 2019-12-18 | 2019-12-19 | 26 | 2 |  | 0%
| Company Registration status | 2019-12-19 | 2019-12-19 | 27 | 1 |  | 0%
| HR Manger Registration | 2019-12-20 | 2019-12-21 | 28 | 2 |  | 0%
| HR Manger Login | 2019-12-21 | 2019-12-21 | 29 | 1 |  | 0%
| HR Manger Forgot password | 2019-12-21 | 2019-12-21 | 29 | 1 |  | 0%
| HR Manger Change Password | 2019-12-21 | 2019-12-21 | 29 | 1 |  | 0%
| HR Manger Account Settings | 2019-12-23 | 2019-12-26 | 31 | 4 |  | 0%
| Create Hr | 2019-12-26 | 2019-12-26 | 34 | 1 |  | 0%
| Upload employee Email id's | 2019-12-27 | 2019-12-27 | 35 | 1 |  | 0%
| View Scholarship Request | 2019-12-28 | 2019-12-28 | 36 | 1 |  | 0%
| Approve or Reject Scholarship Request | 2019-12-30 | 2019-12-30 | 38 | 1 |  | 0%
| Approved Student and reject student list | 2019-12-31 | 2019-12-31 | 39 | 1 |  | 0%
| Payment Gatway integration | 2020-01-01 | 2020-01-02 | 40 | 2 |  | 0%
| Payment History | 2020-01-03 | 2020-01-03 | 42 | 1 |  | 0%
| Due amount detail | 2020-01-04 | 2020-01-04 | 43 | 1 |  | 0%
Government employee
Finance Department
| Login | 2020-01-06 | 2020-01-07 | 45 | 2 |  | 0%
| Forgot password | 2020-01-07 | 2020-01-07 | 46 | 1 |  | 0%
| Change passowrd | 2020-01-07 | 2020-01-07 | 46 | 1 |  | 0%
| Account settings | 2020-01-08 | 2020-01-08 | 47 | 1 |  | 0%
| Bulk Upload the UTR No. and Company Unique ID No | 2020-01-09 | 2020-01-09 | 48 | 1 |  | 0%
| Upload individual company payment status. | 2020-01-09 | 2020-01-09 | 48 | 1 |  | 0%
| View list of completed payment | 2020-01-10 | 2020-01-10 | 49 | 1 |  | 0%
| View list of payment Completed | 2020-01-10 | 2020-01-10 | 49 | 1 |  | 0%
| Send a reminder to payment pendding companies | 2020-01-10 | 2020-01-10 | 49 | 1 |  | 0%
Verification Department
| Login | 2020-01-06 | 2020-01-07 | 45 | 2 |  | 0%
| Forgot password | 2020-01-07 | 2020-01-07 | 46 | 1 |  | 0%
| Change passowrd | 2020-01-07 | 2020-01-07 | 46 | 1 |  | 0%
| Account settings | 2020-01-08 | 2020-01-09 | 47 | 2 |  | 0%
| View list of Scholar Request | 2020-01-10 | 2020-01-10 | 49 | 1 |  | 0%
| Post Verification Employee will approve / reject | 2020-01-11 | 2020-01-11 | 50 | 1 |  | 0%
Report
| View / Download Total No. Of approved Scholars. | 2020-01-13 | 2020-01-13 | 52 | 1 |  | 0%
| View / Download Total No. Of rejected scholars. | 2020-01-13 | 2020-01-13 | 52 | 1 |  | 0%
| Download the graph reports in PDF format | 2020-01-14 | 2020-01-15 | 53 | 2 |  | 0%
Super Admin
| Login | 2020-01-13 | 2020-01-13 | 52 | 1 |  | 0%
| Forgot password | 2020-01-13 | 2020-01-13 | 52 | 1 |  | 0%
| Change passowrd | 2020-01-13 | 2020-01-13 | 52 | 1 |  | 0%
| Account settings | 2020-01-14 | 2020-01-15 | 53 | 2 |  | 0%
| Add, edit, Delete Govt Employees | 2020-01-16 | 2020-01-17 | 55 | 2 |  | 0%
| Student Management | 2020-01-17 | 2020-01-18 | 56 | 2 |  | 0%
| Company Mangement | 2020-01-18 | 2020-01-18 | 57 | 1 |  | 0%
| Govt Employee management | 2020-01-18 | 2020-01-18 | 57 | 1 |  | 0%
Report
| Total Scholarship Request | 2020-01-16 | 2020-01-16 | 55 | 1 |  | 0%
| Aproved Scholarship | 2020-01-17 | 2020-01-17 | 56 | 1 |  | 0%
| Rejected Scholarship | 2020-01-18 | 2020-01-18 | 57 | 1 |  | 0%
| Pending Scholarship | 2020-01-18 | 2020-01-18 | 57 | 1 |  | 0%
Testing
| Employee Module Testing | 2019-12-13 | 2019-12-14 | 21 | 2 |  | 0%
| School Module Testing | 2019-12-18 | 2019-12-21 | 26 | 4 |  | 0%
| Company Module Testing | 2020-01-05 | 2020-01-08 | 44 | 4 |  | 0%
| Govt Employee Module Testing | 2019-12-15 | 2019-12-18 | 23 | 4 |  | 0%
| Super admin Module Testing | 2019-12-19 | 2019-12-21 | 27 | 3 |  | 0%

## Gantt Chart w % Complete
RADTEL
| TASK NAME | START DATE | DAY OF MONTH* | END DATE | DURATION* (WORK DAYS) | DAYS COMPLETE* | DAYS REMAINING* | TEAM MEMBER | PERCENT COMPLETE | WEEK 1 | WEEK 2 | WEEK 3 | WEEK 4
First Sample Project
| Write Landing Page Copy | 2018-01-05 | 5 | 2018-01-08 | 3 | 3 | 0 | Nathan | 100%
| Approve Page Copy | 2018-01-08 | 8 | 2018-01-11 | 3 | 2.4 | 0.6 | Meredith | 80%
| Review Landing Page Design | 2018-01-11 | 11 | 2018-01-16 | 5 | 3 | 2 | Brandon | 60%
| Build Landing Page | 2018-01-14 | 14 | 2018-01-19 | 5 | 2 | 3 | Michael | 40%
| Code Review Landing Page | 2018-01-17 | 17 | 2018-01-23 | 6 | 1.2 | 4.8 | Rachel | 20%
Second Sample Project
| Write Promotional Email | 2018-01-09 | 9 | 2018-01-12 | 3 | 3 | 0 | Nathan | 100%
| Design Promotional Email | 2018-01-12 | 12 | 2018-01-19 | 7 | 5.6 | 1.4 | Meredith | 80%
| Send Promotional Email | 2018-01-17 | 17 | 2018-01-19 | 2 | 1.2 | 0.8 | Brandon | 60%
| Analyze Campaign Results | 2018-01-22 | 22 | 2018-01-26 | 4 | 1.6 | 2.4 | Michael | 40%
Third Sample Project
| Plan Agenda for Meeting | 2018-01-15 | 15 | 2018-01-19 | 4 | 4 | 0 | Nathan | 100%
| Reserve Room | 2018-01-22 | 22 | 2018-01-23 | 1 | 0.8 | 0.2 | Meredith | 80%
| Finalize Presentation | 2018-01-22 | 22 | 2018-01-26 | 4 | 2.4 | 1.6 | Brandon | 60%
| Approve Presentation | 2018-01-26 | 26 | 2018-01-29 | 3 | 1.2 | 1.8 | Michael | 40%
| Create Invitations | 2018-01-22 | 22 | 2018-01-25 | 3 | 0.6 | 2.4 | Rachel | 20%
Fourth Sample Project
| Rewrite Online Calculator | 2018-01-15 | 15 | 2018-01-24 | 9 | 9 | 0 | Nathan | 100%
| Code Review Calculator | 2018-01-25 | 25 | 2018-01-30 | 5 | 4 | 1 | Meredith | 80%
| Update Messaging | 2018-01-24 | 24 | 2018-01-30 | 6 | 3.6 | 2.4 | Michael | 60%
| Publish Calculator | 2018-01-30 | 30 | 2018-01-31 | 1 | 0 | 1 | Rachel | 0%

## Manual Chart
GANTT CHART TEMPLATE
| TASK NAME | START DATE | END DATE | DURATION (WORK DAYS) | TEAM MEMBER | PERCENT COMPLETE | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
[7 empty] | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F
First Sample Project
| Write Landing Page Copy | 2018-01-05 | 2018-01-08 | 3 | Nathan | 100%
|  |  |  | 0 | Meredith | 80% | bar: WEEK 2 M to WEEK 2 T
| Review Landing Page Design | 2018-01-11 | 2018-01-16 | 5 | Brandon | 60% | bar: WEEK 1 F to WEEK 2 Th
| Build Landing Page | 2018-01-14 | 2018-01-19 | 5 | Michael | 40% | bar: WEEK 2 T to WEEK 3 M
| Code Review Landing Page | 2018-01-17 | 2018-01-21 | 4 | Rachel | 20% | bar: WEEK 2 Th to WEEK 3 W
| Promote Landing Page | 2018-01-20 | 2018-01-23 | 3 | Annie | 10% | bar: WEEK 3 T to WEEK 3 Th
Second Sample Project
| Write Promotional Email | 2018-02-05 | 2018-02-08 | 3 | Nathan | 100%
| Design Promotional Email | 2018-02-08 | 2018-02-13 | 5 | Meredith | 80%
| Send Promotional Email to Contacts | 2018-02-11 | 2018-02-16 | 5 | Michael | 60%
| Analyze Results of Email Campagin | 2018-02-14 | 2018-02-23 | 9 | Annie | 40%
Third Sample Project
| Plan Agenda for Team Meeting | 2018-03-05 | 2018-03-08 | 3 | Rachel | 100%
| Reserve Room and Resources for Meeting | 2018-03-08 | 2018-03-13 | 5 | Michael | 80%
| Finalize Team Presentation | 2018-03-11 | 2018-03-16 | 5 | Brandon | 60%
| Review & Approve Presentation | 2018-03-14 | 2018-03-19 | 5 | Meredith | 40%
| Create Invitations for Meeting | 2018-03-17 | 2018-03-21 | 4 | Annie | 20%
| Setup Room for Meeting | 2018-03-20 | 2018-03-25 | 5 | Nathan | 10%
Fourth Sample Project
| Rewrite Code for Online Calculator | 2018-04-05 | 2018-04-08 | 3 | Nathan | 100%
| Code Review Updated Calculator | 2018-04-08 | 2018-04-10 | 2 | Meredith | 80%
| Update Messaging for Calculator | 2018-04-11 | 2018-04-16 | 5 | Michael | 60%
| Publish New Calculator to Site | 2018-04-14 | 2018-04-18 | 4 | Rachel | 40%